## Folha1
Task | Start Date | Days
Initial Study of Project's Objectives | 2019-10-28 | 7
Project Planning | 2019-11-04 | 6
Information Architecture | 2019-11-05 | 4 | 43766
WebApp Mockups | 2019-11-06 | 3
Effort Estimation | 2019-11-07 | 2
Write Specification Report | 2019-11-08 | 4
Development Environment Setup | 2019-11-12 | 6
Interoperability of Database with Backend Server | 2019-11-18 | 15
Specification and Development of Web Routes | 2019-11-21 | 15
Homepage + Login Development | 2019-11-24 | 8
Order List Development | 2019-11-22 | 27
Subscription List Development | 2019-11-22 | 27
Brands Development | 2019-11-25 | 23
Make presentation PowerPoint | 2019-12-10 | 5
Write the Final Report | 2019-12-19 | 3